## 1. The hierarchy

In Jira Scrum, think of the work like this:

Project → Epic → User Story → Task/Bug → Sub-task

And separately:

Backlog → Sprint → Work on issues → Testing → Done

For the project,

### Project

Student Course Registration System

### Epics

- User Authentication

- Course Management

- Course Registration

### User Stories

Under User Authentication:

- Student Registration

- Student Login

- Student Logout

Under Course Management:

- View Available Courses

- View Course Details

Under Course Registration:

- Register for a Course

- View Registered Courses

- Cancel Course Registration

# 2. Create a Jira project

- Open Jira.

- Click Projects.

- Select Create project.

- Select Scrum template.

- Choose Software Development if Jira asks for the project type.

- Enter project name:

Student Course Registration System

- Create the project.

Scrum project contains a Backlog and Active Sprint area.

# 3. Create the Product Backlog

The Product Backlog contains everything that needs to be developed.

| Priority | Item |
| --- | --- |
| High | Student Registration |
| High | Student Login |
| High | Student Logout |
| High | View Courses |
| High | View Course Details |
| High | Register for Course |
| Medium | View Registered Courses |
| Medium | Cancel Course Registration |

Note:- Don't immediately put everything into a Sprint.

The backlog is the complete list of work, while a Sprint contains the work you decide to complete during a particular period.

# 4. Create Epics

Go to Backlog and create Epics.

### Epic 1: User Authentication

Purpose: Everything related to student account access.

Stories:

- Register as Student

- Login as Student

- Logout

### Epic 2: Course Management

Purpose: Allow students to see available courses.

Stories:

- View Available Courses

- View Course Details

### Epic 3: Course Registration

Purpose: Allow students to register for courses.

Stories:

- Register for Course

- View Registered Courses

- Cancel Course Registration

# 5. Create User Stories

Create the actual requirements.

A good User Story format:

As a [user], I want [function], so that [benefit].

For example:

### Story 1 — Student Registration

Summary:

As a student, I want to register an account so that I can use the course registration system.

Possible acceptance criteria:

- Student can enter name.

- Student can enter email.

- Student can enter password.

- Student can confirm password.

- System validates required fields.

- System creates the student account.

- Student receives successful registration message.

- Duplicate email should not be accepted.

### Story 2 — Student Login

Summary:

As a student, I want to log in so that I can access my account.

Acceptance criteria:

- Student enters email.

- Student enters password.

- System validates credentials.

- Correct credentials allow login.

- Incorrect credentials show an error.

- Successful login takes the student to the dashboard.

### Story 3 — View Courses

Summary:

As a student, I want to view available courses so that I can choose a course.

Acceptance criteria:

- Student can see available courses.

- Course name is displayed.

- Course code is displayed.

- Course description is displayed.

- Course availability is displayed.

### Story 4 — Register for Course

Summary:

As a student, I want to register for a course so that I can enroll in the course.

Acceptance criteria:

- Logged-in student can select a course.

- Student can click Register.

- System checks course availability.

- Student is registered successfully.

- Confirmation message is displayed.

- Student can see the registered course.

# 6. Create Issues

In Jira, Story, Task, Bug, and Sub-task are different issue types.

For project, the main requirements should normally be Stories.

And can also create Tasks for technical work.

For example:

### Story

Student Login

technical Tasks might be:

- Create login UI

- Implement login API

- Implement authentication validation

- Connect login UI to API

Or can keep these as Sub-tasks under the Story, depending on how the team wants to manage the work.

# 7. Create Sub-tasks

This is an important part of the Jira demonstration.

Suppose:

Story: Student Registration

Create these Sub-tasks:

- Create registration page UI

- Create registration form validation

- Create student database table

- Implement registration API

- Connect registration page with API

- Test registration functionality

So the hierarchy looks like:

EPIC: User Authentication

|

+-- STORY: Student Registration

|       |

|       +-- SUB-TASK: Create registration UI

|       +-- SUB-TASK: Form validation

|       +-- SUB-TASK: Create database table

|       +-- SUB-TASK: Registration API

|       +-- SUB-TASK: Connect UI and API

|       +-- SUB-TASK: Test registration

|

+-- STORY: Student Login

|

+-- SUB-TASK: Create login UI

+-- SUB-TASK: Login validation

+-- SUB-TASK: Authentication API

+-- SUB-TASK: Test login

# 8. Add Story Points

Story Points estimate how difficult a story is.

A common scale is:

1, 2, 3, 5, 8, 13

For example:

| Story | Story Points |
| --- | --- |
| Student Registration | 5 |
| Student Login | 3 |
| Student Logout | 1 |
| View Courses | 3 |
| View Course Details | 2 |
| Register for Course | 5 |
| View Registered Courses | 3 |
| Cancel Registration | 3 |

Don't treat story points as exact hours. They represent relative complexity/effort.

# 9. Set Priority

Give each story a priority.

For example:

### Highest priority

- Student Registration

- Student Login

- View Courses

- Register for Course

### Medium priority

- View Course Details

- View Registered Courses

- Cancel Registration

### Low priority

- Student Logout

This helps the Product Owner decide what should be developed first.

# 10. Add Acceptance Criteria

Every important User Story should have clear acceptance criteria.

For example:

### Register for Course

Acceptance Criteria

Given the student is logged in

When the student selects an available course

And clicks "Register"

Then the student should be registered for that course

And a confirmation message should be displayed.

This can be added in Jira's Description field.

# 11. Create Sprint 1

Now, Product Backlog is ready.

Go to:

Backlog → Create Sprint

Call it:

Sprint 1 – Authentication

For example, Sprint 1 could contain:

- Student Registration — 5 points

- Student Login — 3 points

- Student Logout — 1 point

Total: 9 Story Points

Move these stories from the Product Backlog into Sprint 1.

# 12. Set Sprint Goal

A Sprint should have a clear goal.

For Sprint 1:

Sprint Goal: Implement basic student registration and login functionality.

This is useful when explaining Scrum in an interview, viva, or project presentation.

# 13. Start the Sprint

Click:

Start Sprint

Set:

- Sprint name: Sprint 1

- Duration: for example, 2 weeks

- Sprint Goal: Implement student registration and login

Then start the Sprint.

Your Jira board will typically have columns such as:

TO DO → IN PROGRESS → DONE

# 14. Developer starts working

Suppose the developer starts:

Student Registration

Move the Story:

TO DO

↓

IN PROGRESS

Then work on its Sub-tasks.

For example:

Create Registration UI

↓

IN PROGRESS

↓

DONE

Then:

Registration API

↓

IN PROGRESS

↓

DONE

# 15. Testing

Testing should also be part of the workflow.

For example:

Developer completes Registration

↓

Tester tests Registration

↓

Pass

↓

DONE

If testing finds a problem, create a Bug.

Example:

### Bug

Summary:

Registration accepts duplicate email addresses

Description:

When a student registers using an email address that already exists, the system creates another account instead of displaying an error.

Priority:

High

The Bug can be assigned to the developer.

# 16. Example complete Jira structure

Your Jira project can eventually look like this:

PROJECT

Student Course Registration System

│

├── EPIC: User Authentication

│   │

│   ├── STORY: Student Registration

│   │   ├── SUB-TASK: Registration UI

│   │   ├── SUB-TASK: Form Validation

│   │   ├── SUB-TASK: Database

│   │   ├── SUB-TASK: Registration API

│   │   └── SUB-TASK: Registration Testing

│   │

│   ├── STORY: Student Login

│   │   ├── SUB-TASK: Login UI

│   │   ├── SUB-TASK: Login Validation

│   │   ├── SUB-TASK: Login API

│   │   └── SUB-TASK: Login Testing

│   │

│   └── STORY: Student Logout

│

├── EPIC: Course Management

│   │

│   ├── STORY: View Available Courses

│   └── STORY: View Course Details

│

└── EPIC: Course Registration

│

├── STORY: Register for Course

│   ├── SUB-TASK: Registration UI

│   ├── SUB-TASK: Availability Check

│   ├── SUB-TASK: Registration API

│   └── SUB-TASK: Testing

│

├── STORY: View Registered Courses

└── STORY: Cancel Course Registration

# 17. Sprint 2

After Sprint 1, create the next Sprint.

### Sprint 2 Goal

Implement course viewing and course registration.

Move these stories into Sprint 2:

- View Available Courses — 3

- View Course Details — 2

- Register for Course — 5

Total:

10 Story Points

Then:

Start Sprint → Develop → Test → Move issues to Done

# 18. Sprint 3

### Sprint 3 Goal

Complete student course management functionality.

Stories:

- View Registered Courses — 3

- Cancel Course Registration — 3

You can also use Sprint 3 for fixing remaining bugs and improving the application.

# 19. Daily Scrum

During the Sprint, the team can conduct a Daily Scrum.

Each team member answers:

### 1. What did I do yesterday?

I completed the student registration API.

### 2. What will I do today?

I will connect the registration API with the UI.

### 3. Are there any blockers?

The database connection is currently not working.

This is not primarily a Jira activity, but Jira's board helps the team see the current work.

# 20. Sprint Review

At the end of the Sprint, conduct a Sprint Review.

For Sprint 1, demonstrate:

### Student Registration

Open application

↓

Click Register

↓

Enter student details

↓

Submit

↓

Account created

### Student Login

Enter email

↓

Enter password

↓

Click Login

↓

Dashboard

Show the completed Jira stories as well.

# 21. Sprint Retrospective

After the Sprint Review, conduct a Sprint Retrospective.

Discuss:

### What went well?

Registration UI was completed on time.

### What did not go well?

Login API took longer than expected.

### What can we improve?

We should define API requirements before starting development.

This is an important Scrum step that beginners often forget.

# 22. Sprint completion

At the end of the Sprint:

Check:

- Completed stories

- Incomplete stories

- Bugs

- Remaining Sub-tasks

- Story Points completed

If a Story isn't finished, don't simply mark it Done.

Move the unfinished work back to the Product Backlog or handle it according to your team's Jira/Scrum process, and plan it for a future Sprint.

# 23. Backlog Refinement

Before the next Sprint, review the backlog.

For each upcoming story:

- Clarify requirements

- Add acceptance criteria

- Estimate Story Points

- Set priority

- Break large stories into smaller stories if necessary

- Identify dependencies

For example:

Register for Course

might need clarification:

Can a student register for the same course twice?

What happens if the course is full?

What happens if registration is closed?

These questions should be resolved before development.

# 24. Definition of Ready

You can also define a Definition of Ready (DoR).

A Story is ready for a Sprint when:

- Requirement is clear

- Acceptance criteria are defined

- Story is small enough

- Dependencies are identified

- Story Points are estimated

- Product Owner has prioritized it

Example:

Register for Course → Ready

# 25. Definition of Done

This is another important thing to include.

A Story is Done only when, for example:

- Code is completed

- Code review is completed

- Unit testing is completed

- Functional testing is completed

- Acceptance criteria pass

- No critical bugs remain

- Documentation is updated if required

- Product Owner accepts the story

So:

Development Complete

↓

Code Review

↓

Testing

↓

Acceptance Criteria Passed

↓

Product Owner Acceptance

↓

DONE

# 26. Reports in Jira

After completing Sprints, Jira can provide Scrum reports.

Useful reports include:

### Burndown Chart

Shows how much work remains in the Sprint.

Remaining Work

|

|\

| \

|  \

|   \

|    \

|_____\

Time

### Velocity Chart

Shows how many Story Points the team completes across Sprints.

Example:

| Sprint | Completed |
| --- | --- |
| Sprint 1 | 9 |
| Sprint 2 | 10 |
| Sprint 3 | 6 |

This helps estimate how much work the team can realistically take into future Sprints.

# 27. Workflow

For the project, the entire process is:

1. Create Jira Scrum Project

↓

2. Create Product Backlog

↓

3. Create Epics

↓

4. Create User Stories

↓

5. Add Acceptance Criteria

↓

6. Set Priority

↓

7. Estimate Story Points

↓

8. Break Stories into Tasks/Sub-tasks

↓

9. Backlog Refinement

↓

10. Create Sprint

↓

11. Set Sprint Goal

↓

12. Move Stories into Sprint

↓

13. Start Sprint

↓

14. Move Issues:

TO DO → IN PROGRESS → DONE

↓

15. Development

↓

16. Testing

↓

17. Create Bugs if required

↓

18. Sprint Review

↓

19. Sprint Retrospective

↓

20. Complete Sprint

↓

21. Review Backlog

↓

22. Start Next Sprint

↓

23. Release Completed Product